## COVER
ATP SERVICE IMPLEMENTATION V3.2
CUSTOMER:
EMPACOR SA
DEAL CODE:
1131484 | LATAM
CARIBBEAN
REGION:
LATAM
SID - IP IMPLEMENTATION Engineer:
DATE:
2022-06-30

## CONFIG
CONFIG-NETWORKING | CONFIG-WIFI
Note on O5: Luz Heidy De La Hoz: Aplica para Onsite Controller y Fortigate (modo route sin UTM).

## ATPs_LOG
ATPs LOGs | ATP WIFI - RETAIL

## TEST_PLAN
TESTPLAN
CHECKLIST
Managed WAN:
Conectivity WAN
|  | Packet loss (ping WAN, sourced, MTU 1500, 1000) | ok
|  | Interface error (show interfaces) | ok
Management
|  | DCN Acesss (ping from DCN/Citrix) | ok
|  | Netcool Ping (ping from CPE to Netcool) | ok
|  | Cacti Ping (ping from CPE to CACTI servers) | ok
BGP test
|  | Advertise routes | n/a
|  | receive routes | n/a
|  | Filtering Configuration (If required) | n/a
|  | Failover test | n/a
Static route test
|  | route Table | ok
MANAGED LAN:
Protocol Test
|  | DHCP (DHCP bindings) | n/a
|  | NAT (Translations, statistics and flow in case of junos) | n/a
|  | TRUNK OPERATION (show int trunk, show vlan) | ok
|  | HSRP/VRRP/GLBP (show standby, show vrrp, show glbp) | n/a
|  | Static (ping to next hop in LAN) | ok
|  | LAG operation (show etherchannel summary) | n/a
|  | MAC LEARNING (show arp table and mac-address table) | ok
MANAGED WI-FI:
Management
|  | Access | n/a
|  | Packet loss | n/a
|  | Ping | n/a
Controller
|  | Ping - Conectivity to Controller | n/a
|  | Failover test (Onsite HA Controller) | n/a
| Access Point |  | n/a
|  | Ping - Conectivity to APs | n/a
|  | Coverage test (based in Onsite testing by Technician and customer) | n/a

## CONFIG_WIFI
WiFI - CONTROL AP VLAN
| Site | VLAN ID | Network | Mask | Gateway | DHCP
LAN MANAGEMENT (SWITCHs AND CONTROLLER)
| Site | VLAN ID | Network | Mask | Gateway | DHCP
WiFi - SSIDs
SSID Name/description | Authentication Method | Info Server RADIUS | VLAN ID | Network | Mask | Gateway | DHCP
RED LAN ACTUAL | RED LAN ACTUAL
Hotel - Sede | Hotel - Sede | VLAN ID | Network | Mask | Gateway | DHCP | DNS
Administrativo | Hotel Panamerican | 1 | 192.168.1.1 | 255.255.255.0 | 192.168.1.2 | 1 | 1
| Hotel Antigua | 1 | 192.168.1.1 | 255.255.255.0 | 192.168.1.2 | 1 | 1
| Hotel Panajachel | 1 | 192.168.10.1 | 255.255.255.0 | 192.168.10.2 | 1 | 1
Huepedes | Hotel Panamerican | 1 | 192.168.10.1 | 255.255.255.0 | 192.168.10.2 | 1 | 1
| Hotel Antigua | 1 | 192.168.10.1 | 255.255.255.0 | 192.168.10.2 | 1 | 1
| Hotel Panajachel | 1 | 192.168.1.1 | 255.255.255.0 | 192.168.1.2 | 1 | 1
AP CONFIGURATION
AP NAME | MODEL | Description/Location | SITE | IP Address | Netmask | Gateway | MAC | Serial

## CONFIG-RETAIL
RETAIL ANALYTICS
CUSTOMER INFORMATION | Customer Name
Address
Telephone
Customer Web Page
Main Contact - User
Contact email
LOGO (Attached)
COLOR - Customer Design Branch
SSID NAME
AUTHENTICACTION METHOD | SOCIAL NETWORKS | USERS | PASSWORD | LIKE | POST
TERMS AND CONDITIONS | DEFAULT | CUSTOM TERMS
URL REDIRECTION | www.sanfernandoplazamedellin.com
ADMINISTRATORS USERS OF THE RETAIL ANALYTICS PORTAL
AP CONFIGURATION
AP Name | Model | Description/Location | IP Address | Netmask | Gateway | MAC | Serial
Note on C12: Color in Hexadecimal code
Note on C14: Name of the SSID where the Retail Analytics portal will be enabled
Note on D16: Administrator User of the Account (Must be a company account)
Note on E16: Password of the Administrator User
Note on F16: Applies only for Facebook.
Note on G16: Applies for Twitter
Note on D21: Especificar los datos importantes que serán solicitados al cliente. Ejemplo: Edad, Genero o Sexo, E-mail
Note on D24: Si se desea utilizar Terminos y Condiciones redactados por el cliente. Favor ingresar el texto.
Note on C26: Escribir URL del sitio donde se redireccionarán los Usuarios WiFi.
Note on F28: Si desean que se asigne un password provisional, para que este luego sea cambiado en el primer login del usuario. Ingresar "Provisional"

## CONFIG-LB
LOCATION BASED
CUSTOMER INFORMATION
ADMINISTRATORS USERS OF THE RETAIL ANALYTICS PORTAL | Name: | E-mail:
| Name: | E-mail:
LOGO (Attached)
CUSTOMER SITE MAP
COORDINATES
POINTS OF INTEREST (INDICATED OVER CUSTOMER SITE MAP)
Note on B12: Ricardo Gamboa: El plano debe ser enviado en alta resolucion. Formato PNG, PDF o JPEG. LA resolución debe ser suficiente para que se conserven los detalles de las lineas diferentes niveles de zoom. No incluir la decoración interior en el plano. No incluir detalles internos de areas que no deban ser accesibles a los visitantes. Incluir escala del plano
Note on B17: Ricardo Gamboa: Latitud y Longuitud del sitio
Note on C18: Ricardo Gamboa: Adjuntar todos los puntos de interes que se consideren necesarios
Note on F18: Ricardo Gamboa: Indicar en plano la ubicación de los puntos de interes